## Start Here
Client Project & Capacity Tracker
One file for every project, every promise, the invoice status you type in, and every free hour you have left.
FIRST 15 MINUTES
0 · Delete the 8 EXAMPLE rows — Projects rows 5–7 and Deliverables rows 5–9. They are filled in so the Dashboard and the colour warnings show something real the moment you open the file.
1 · Projects — type your live jobs: Client, Project, Status, Fee agreed, Due. The Project name in column C is the key of the whole file: the Deliverables dropdown and every per-project total are built from it.
2 · Deliverables — one row per thing you owe. Pick the project from the dropdown, set the Due date and the Planned hours.
3 · Week Capacity — overwrite the 25 h per week with YOUR real available hours, and put holidays into Blocked / time off.
4 · Dashboard — read, never type. Excel locks it read-only; Google Sheets drops that lock on import, so just don't type on it there.
THE FIT CHECK — Week Capacity, top block: type the hours a new enquiry needs and the date the client wants. You get YES / TIGHT / NO with the number behind it. It answers only from the hours YOU entered — it does not estimate how long work takes and does not know your speed.
SET ONCE — Projects row 3: B3 = your payment term in days (default 30), E3 = your target hourly rate (optional). Both drive the colour warnings and nothing else.
GREY MEANS CALCULATED — never type in a grey cell. The white cells and the four yellow ones (Projects B3 and E3, Week Capacity B5 and B6) are yours.
CURRENCY — numbers are currency-neutral on purpose. Want € or $? Select columns I:J and L:N on Projects (skip K, that one is a date) → Format → Currency. Nothing breaks.
PROJECT NAMES — keep them unique and avoid the characters * and ? inside them; they act as wildcards in spreadsheet lookups. The Linked? column on Deliverables flags any name that does not match Projects.
GOOGLE SHEETS — File → Import → Upload → Create new spreadsheet. Formulas, dropdowns and colour rules come across. Three things do not: print settings, the read-only lock on the Dashboard, and a few font details. Set print options once under File → Print.
IF A CALCULATED CELL LOOKS EMPTY ON FIRST OPEN — Excel: press Ctrl+Alt+F9. LibreOffice: Data → Calculate → Recalculate Hard. Google Sheets: recalculates automatically on import.
HONEST LIMITS — this file tracks status only. It does not write, number or send invoices, does not track time in the background, sends no reminders, connects to no bank, invoicing tool or calendar, and calculates no VAT, sales tax or tax of any kind. Not tax, legal or accounting advice.
LICENSE — personal use by one buyer, on all your own devices, for as many of your own client projects as you like. The file holds 60 projects, 300 deliverables and 26 weeks. Please do not resell or redistribute.
Questions or a formula that misbehaves? Message us on Etsy — we answer within 48 hours (1–2 business days).

## Dashboard
Dashboard |  |  | 30
Everything here computes itself — never type on this sheet. All countdowns relative to 2026-07-29
22
THIS WEEK & AHEAD
Free hours this week | Load next 4 weeks | Committed hours this week (incl. overdue)
22 | 32% | 3
PROMISES
Next deadline in days (minus = late) | Deliverables past their due date | Open deliverables
-8 | 1 | 4
Most overdue: Logo concepts (3 routes) · Brand refresh · 8 days late
MONEY (your currency — no tax of any kind is calculated)
Delivered, not invoiced | Older than the payment term you set | Awaiting payment
1 | 2400 | 2400
1 invoice(s) older than the 30-day payment term you set.
Booked 10.000,00 · Invoiced 5.400,00 · Still to invoice 4.600,00 (your currency — no tax of any kind is calculated)
HOW TO READ THIS
Green = room to say yes. Amber = tight, only by moving a date. Red = you are already over; something has to give.
Every number here comes from Projects, Deliverables and Week Capacity. Change a number there and this sheet follows.
Print: set up for one portrait page (A1:H24). Google Sheets does not import print settings — set them once under File → Print.

## Projects
Projects
One row per client project. Amounts live here and nowhere else. Grey columns calculate themselves — never type in them.
Payment term (days) → | 30 |  | Target rate / hour → |  | optional — turns 'Rate / hour so far' amber whenever it drops below this
# | Client | Project | Service type | Status | Started | Due (final) | Days left | Fee agreed | Invoiced | Invoiced on | Paid | Still to invoice | Awaiting payment | Days since invoice | Hours quoted | Hours logged | Hours left | Rate / hour so far | Deliverables done | Notes
1 | EXAMPLE — delete this row | Brand refresh | Design | In progress | 2026-07-05 | 2026-08-14 | 16 | 4800 | 2400 | 2026-06-21 |  | 2400 | 2400 | 38 | 40 | 5 | 35 | 960 | 0 / 2 | First invoice is older than the payment term — see the red cell in column O.
2 | EXAMPLE — delete this row | Website copy | Copywriting | Booked | 2026-07-23 | 2026-08-25 | 27 | 2200 |  |  |  | 2200 | — | — | 18 | 2 | 16 | 1100 | 0 / 1 | Nothing invoiced yet — column M shows what is still to invoice.
3 | EXAMPLE — delete this row | Q3 retainer | Retainer | In progress | 2026-06-07 | 2026-08-07 | 9 | 3000 | 3000 | 2026-07-17 | 3000 | 0 | 0 | — | 24 | 6 | 18 | 500 | 1 / 2 | Fully invoiced and paid — columns N and O go quiet.
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
[7 empty] | — |  |  |  |  | — | — | — |  | — | — | — | —
Formulas:
Days left = IF([Due (final)]="","—",IF(OR([Status]="Approved",[Status]="Closed",[Status]="Cancelled"),"—",IFERROR(INT([Due (final)])-TODAY(),"—")))
Days since invoice = IF([Invoiced on]="","—",IF(NOT(ISNUMBER([Awaiting payment])),"—",IF([Awaiting payment]<=0,"—",IFERROR(TODAY()-INT([Invoiced on]),"—"))))

## Deliverables
Deliverables
One row per thing you owe. Due date and Planned hours here become the weekly load on Week Capacity.
Fill in Projects first — this dropdown builds itself from Projects, column C.
# | Project | Linked? | Deliverable / milestone | Due date | Status | Planned hours | Hours logged | Hours left | Days left | Week (Mon) | Invoice status | Deadline | Waiting on | Notes
1 | Brand refresh | ✓ | Logo concepts (3 routes) | 2026-07-21 | In progress | 8 | 5 | 3 | -8 | 2026-07-20 | Not yet | Hard date | Me | EXAMPLE — delete. Past its due date, so it turns red and carries into this week.
2 | Brand refresh | ✓ | Brand guidelines PDF | 2026-08-09 | Not started | 12 |  | 12 | 11 | 2026-08-03 | Not yet | Can move | Me | EXAMPLE — delete. 'Can move' means the Fit Check may shift it out of a full week.
3 | Website copy | ✓ | Homepage + 4 subpages | 2026-08-03 | In progress | 10 | 2 | 8 | 5 | 2026-08-03 | Not yet | Hard date | Client | EXAMPLE — delete.
4 | Q3 retainer | ✓ | July social set | 2026-07-20 | Delivered | 6 | 6 | — | — | 2026-07-20 | Not yet | Can move | Client | EXAMPLE — delete. Delivered but not invoiced — the amber cell in column L is money you have not billed.
5 | Q3 retainer | ✓ | August campaign brief | 2026-08-16 | Not started | 9 |  | 9 | 18 | 2026-08-10 | Not yet | Can move | Me | EXAMPLE — delete.
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
[8 empty] | — | — | —
Formulas:
Days left = IF([Due date]="","—",IF(OR([Status]="Delivered",[Status]="Approved",[Status]="Cancelled"),"—",IFERROR(INT([Due date])-TODAY(),"—")))
Week (Mon) = IF([Due date]="","—",IFERROR(INT([Due date])-WEEKDAY(INT([Due date]),3),"—"))

## Week Capacity
Week Capacity & Fit Check
26 weeks, rolling from this Monday. You type only in Available hours, Blocked / time off, Note — and in the two yellow Fit Check cells.
FIT CHECK — a new enquiry just landed: can you take it?
Hours the new job needs →
Wanted delivery date →
That week starts (Mon) | —
Free hours in that week | —
Free hours before that week | —
Movable work in that week | —
VERDICT | Enter hours and a date above.
Overdue hours carried into this week | 3
Table starts (Mon) | 2026-07-27 | type any date over this to freeze the window — the table snaps to that week's Monday
Week starting (Mon) | Week | Available hours | Committed hours | Blocked / time off | Free hours | Load | Movable hours | Open deadlines | Note
2026-07-27 | Week 31 | 25 | 3 |  | 22 | 12% | 0 | 0
2026-08-03 | Week 32 | 25 | 20 |  | 5 | 80% | 12 | 2
2026-08-10 | Week 33 | 25 | 9 |  | 16 | 36% | 9 | 1
2026-08-17 | Week 34 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-08-24 | Week 35 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-08-31 | Week 36 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-09-07 | Week 37 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-09-14 | Week 38 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-09-21 | Week 39 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-09-28 | Week 40 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-10-05 | Week 41 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-10-12 | Week 42 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-10-19 | Week 43 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-10-26 | Week 44 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-11-02 | Week 45 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-11-09 | Week 46 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-11-16 | Week 47 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-11-23 | Week 48 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-11-30 | Week 49 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-12-07 | Week 50 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-12-14 | Week 51 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-12-21 | Week 52 | 25 | 0 |  | 25 | 0% | 0 | 0
2026-12-28 | Week 53 | 25 | 0 |  | 25 | 0% | 0 | 0
2027-01-04 | Week 1 | 25 | 0 |  | 25 | 0% | 0 | 0
2027-01-11 | Week 2 | 25 | 0 |  | 25 | 0% | 0 | 0
2027-01-18 | Week 3 | 25 | 0 |  | 25 | 0% | 0 | 0
Row 1 of this table also carries everything that is already overdue — late work still costs hours.
Formulas:
Week starting (Mon) = [Week starting (Mon), row above]+7
Week = IFERROR("Week "&TEXT(WEEKNUM([Week starting (Mon)],21),"0"),"—")

## Lists
Consulting | Lead | Not started | Not yet | Hard date | Me
Design | Quoted | In progress | Ready to invoice | Can move | Client
Development | Booked | With client | Invoiced |  | Subcontractor
Copywriting | In progress | Delivered | Paid
Editing | With client | Approved
Translation | Delivered | Blocked
Photography | Approved | Cancelled
Video | On hold
Marketing | Cancelled
Training | Closed
Retainer
Other
These six columns feed every dropdown in this file.
A = Service type · B = Project status · C = Deliverable status · D = Invoice status · E = Deadline · F = Waiting on
Rename an entry here and the dropdown follows — but rename it in the sheets too, or the colour rules stop matching.
To ADD an entry, type it in the next free cell of that column, then widen the range under Data → Data validation.
Leave no empty cells inside a column — a gap creates an empty line in the dropdown.