## Start Here
Dissertation Writing Tracker
You can see, every time you open it, whether you are on pace to finish.
HOW TO USE THIS WORKBOOK
1 · Chapters — one row per chapter: name, word goal, due date, status. Writing something that already has words? Put them in 'Starting words' — progress starts from there.
2 · Writing Sessions — after every session, one row: date, chapter, minutes, words. Cut more than you wrote? Negative numbers are allowed. 20 seconds of logging, that's the whole habit.
3 · Dashboard — your pace, live: total words vs. goal, words per day needed, this week vs. last week, your streak, the next deadlines. Never type in a grey cell — grey means it calculates itself.
4 · Revisions — one row per feedback round (R1–R4): who it came from, when it's due, where it stands.
5 · Submission & Defense — type your submission deadline into C5 and your defense date into C6. The submission and defense countdowns (and words/day needed) hang off these two cells. Below: the last-mile checklist.
6 · Lists — all dropdown values, visible and yours to edit.
GOOGLE SHEETS: File → Import → Upload this file. Formulas, dropdowns and colours all survive the trip.
CAPACITY — 25 chapters, 300 writing sessions, 100 revision rounds. Always type into the next empty (pre-filled) row — do not insert new rows: inserted rows have no grey formulas, and rows beyond the capacity are not counted. Duplicate the file per thesis.
DEMO DATA — the file ships with 5 example chapters and 14 example sessions whose dates move with today, so the Dashboard is alive when you open it. Before you start, delete the CONTENTS of these cells (select them and press Delete — never delete whole rows): Chapters rows 5–9, Writing Sessions rows 5–18, Revisions rows 5–7, the two demo dates on Submission & Defense (C5, C6), and reset the three demo checklist statuses (E11, E13, E15) to 'Not started'.
NAMING — give every chapter a unique name and avoid *, ? and ~ in names: sessions are matched to chapters by their exact name (~ is the SUMIF/COUNTIF escape character).
STREAK — consecutive calendar days with at least one logged session, ending today; yesterday keeps it alive until you log today. Counts up to 30.
PRINTING — print areas are set on every sheet. Google Sheets ignores imported print areas: File → Print → 'Selected cells' → Fit to width.
LICENSE — Personal use. One buyer, unlimited own projects & devices. Please don't resell or redistribute.
Questions or a broken formula? Message us on Etsy — we reply within 48 h.

## Dashboard
Dashboard
Your pace, live — every number updates itself from the other sheets. Never type here.
PACE
| Total words written | Total word goal | % of goal | Words/day needed | Days to submission
| 23420 | 50000 | 46.84% | 292 | 91
THIS WEEK
| Words this week | Words last week | Sessions this week | Minutes this week | Days to defense
| 4620 | 4450 | 6 | 465 | 105
MOMENTUM
| Writing streak (days) | Active days — last 7 | Best session (words) | Avg words / session | Next revision due (days)
| 5 | 6 | 1150 | 766 | 4
| CHAPTERS |  |  |  |  | NEXT CHAPTER DEADLINES
| Chapter | Goal | Written | % | Status | Chapter | Due | Days
| Introduction | 8000 | 7690 | 96.12% | Revising | Introduction | 2026-08-16 | 14
| Literature Review | 12000 | 10580 | 88.17% | Drafting | Literature Review | 2026-08-30 | 28
| Methodology | 10000 | 5150 | 51.5% | Drafting | Methodology | 2026-09-20 | 49
| Results | 9000 | 0 | 0% | Outlining
| Discussion & Conclusion | 11000 | 0 | 0% | Not started
Never type on this sheet — it computes itself.

## Chapters
Chapters
One row per chapter. Words written pulls itself from your session log — the bar fills as you write. Grey columns calculate themselves.
# | Chapter | Word goal | Due date | Status | Starting words | Words written (auto) | % done (auto) | Days left (auto) | Progress (auto) | Sort key (auto)
1 | Introduction | 8000 | 2026-08-16 | Revising | 4200 | 7690 | 96.12% | 14 | █████████░ | 2026-08-16
2 | Literature Review | 12000 | 2026-08-30 | Drafting | 5600 | 10580 | 88.17% | 28 | ████████░░ | 2026-08-30
3 | Methodology | 10000 | 2026-09-20 | Drafting | 2900 | 5150 | 51.5% | 49 | █████░░░░░ | 2026-09-20
4 | Results | 9000 | 2026-10-11 | Outlining |  | 0 | 0% | 70 | ░░░░░░░░░░ | 2026-10-11
5 | Discussion & Conclusion | 11000 | 2026-11-01 | Not started |  | 0 | 0% | 91 | ░░░░░░░░░░ | 2026-11-01
Formulas:
Days left (auto) = IF([Chapter]="","",IF([Status]="Final","—",IFERROR(IF([Due date]="","—",[Due date]-TODAY()),"—")))
Sort key (auto) = IF([Chapter]="","",IF([Status]="Final","",IF(ISNUMBER([Due date]),[Due date]+ROW()/100000,"")))

## Writing Sessions
Writing Sessions
One row per session — date, chapter, minutes, words. The demo rows use live dates so they never look stale; clear the contents of rows 5–18 before you start (don't delete the rows).
# | Date | Chapter | Minutes | Words written | Week (auto) | Note
1 | 2026-08-02 | Introduction | 90 | 850 | W31 | Tightened section 1.2
2 | 2026-08-01 | Introduction | 60 | 700 | W31 | New opening
3 | 2026-07-31 | Literature Review | 120 | 1100 | W31 | Theory block
4 | 2026-07-30 | Methodology | 45 | 400 | W31 | Sampling section
5 | 2026-07-29 | Literature Review | 90 | 950 | W31
6 | 2026-07-27 | Methodology | 60 | 620 | W31
7 | 2026-07-26 | Introduction | 75 | 800 | W30
8 | 2026-07-25 | Literature Review | 100 | 1000 | W30
9 | 2026-07-24 | Methodology | 30 | 350 | W30 | Short but counts
10 | 2026-07-22 | Literature Review | 80 | 780 | W30
11 | 2026-07-21 | Introduction | 60 | 640 | W30
12 | 2026-07-20 | Methodology | 90 | 880 | W30
13 | 2026-07-19 | Literature Review | 110 | 1150 | W29 | Best day so far
14 | 2026-07-17 | Introduction | 45 | 500 | W29
Formulas:
Week (auto) = IF([Date]="","",IFERROR("W"&TEXT(WEEKNUM([Date],21),"00"),""))

## Revisions
Revisions
One row per feedback round. 'Submitted' and 'Done' silence the countdown — open rounds stay loud until they are back.
# | Chapter | Round | Feedback from | Received | Due | Status | Days left (auto) | Notes | Sort key (auto)
1 | Introduction | R1 | Advisor | 2026-07-23 | 2026-08-06 | In progress | 4 | Ch. 1 comments from advisor | 2026-08-06
2 | Literature Review | R1 | Peer | 2026-07-27 | 2026-08-11 | Not started | 9 | Peer read of theory section | 2026-08-11
3 | Methodology | R1 | Self | 2026-07-13 | 2026-07-18 | Done | — | Self-edit pass
Formulas:
Days left (auto) = IF([Chapter]="","",IF(OR([Status]="Submitted",[Status]="Done"),"—",IFERROR(IF([Due]="","—",[Due]-TODAY()),"—")))
Sort key (auto) = IF([Chapter]="","",IF(OR([Status]="Submitted",[Status]="Done"),"",IF(ISNUMBER([Due]),[Due]+ROW()/100000,"")))

## Submission & Defense
Submission & Defense
The last mile on one page. The Dashboard counts down from C5 (submission) and C6 (defense).
KEY DATES
| Final submission deadline | 2026-11-01 | 91
| Defense date | 2026-11-15 | 105
| Post-defense revisions due |  | —
CHECKLIST
| Task | Due | Days | Status | Notes
| University formatting & template check |  | — | In progress
| Title page, abstract & front matter |  | — | Not started
| Citations & reference list complete |  | — | In progress
| Figures, tables & appendices numbered |  | — | Not started
| Plagiarism self-check run |  | — | Done
| Advisor sign-off on final draft |  | — | Not started
| Submission logistics (upload, printing, forms) |  | — | Not started
| Committee scheduling & paperwork |  | — | Not started
| Defense presentation drafted |  | — | Not started
| Defense practice run |  | — | Not started
| Post-defense revisions submitted |  | — | Not started
| Final deposit / archive copy |  | — | Not started
| Checklist progress | 1 of 12 done
Formulas:
Days = IF([Task]="","",IF(OR([Status]="Done",[Status]="N/A"),"—",IFERROR(IF([Due]="","—",[Due]-TODAY()),"—")))

## Lists
Not started | R1 | Advisor | Not started | Not started | This sheet feeds the dropdowns. Edit values here if you must — keep them short, the colours key on the exact text.
Outlining | R2 | Committee | In progress | In progress
Drafting | R3 | Peer | Submitted | Done
Revising | R4 | Self | Done | N/A
Final